## Comm Plan Exemplar
Beta "T.B": Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 10 AM | In Person | Discuss project progress, task updates, and ensure team stays on track for the delivery improvement plan. | ------------- | -------------
Technical Manager & HR Manager | Improvement Progress Meeting | Weekly | Project Manager | Fridays at 3 PM | In Person/Online | Review progress of modern devices purchase, new hires, and work distribution system implementation. | ------------- | -------------
IT Team | System Development Check-In | Weekly | Project Manager | Tuesdays at 2 PM | In Person/Online | Review progress of work distribution system, call reception upgrades, and AI-powered software development. | ------------- | -------------
Operations & Sales Managers | Operational Performance Meeting | Weekly | Project Manager | Mondays at 11 AM | In Person | Monitor on-time order arrivals, customer service, and address any operational challenges. | ------------- | -------------
HR Manager | Hiring & Training Updates | Weekly | HR Manager | Wednesdays at 1 PM | Email/Phone Call | Provide updates on hiring additional workers and call receptionists; review training session schedules. | ------------- | -------------
Training Manager | Training Progress Report | Bi-Weekly | Training Manager | Wednesdays and Fridays | Email/Phone Call | Provide updates on the progress of delivery worker training on efficient routes and time management. | ------------- | -------------
Facilities (for employee training) | Facilities Reservation Check-In | One-time | Administrative Coordinator | One week before the training | Phone Call | Ensure rooms, spaces, and equipment are reserved for delivery worker training. | ------------- | -------------
Marketing & Data Analysts | Performance and Feedback Review | Bi-Weekly | Business Analyst & Data Analyst | Every other Thursday | In Person/Online | Review KPIs and performance data; analyze customer feedback trends. | ------------- | -------------
Delivery Team & Operations Manager | Delivery Performance Updates | Weekly | Sales & Operations Managers | Thursdays at 3 PM | Phone Call/In Person | Ensure timely deliveries, follow up with the delivery team, and address any performance gaps. | ------------- | -------------
Customers | Feedback Survey | One-time | Marketing Team | First business day after delivery improvements | Email | Solicit feedback on delivery service improvements and customer satisfaction. | ------------- | -------------
Your Manager | Status Update | Weekly | Project Manager | Mondays at 2 PM | In Person | Provide updates on overall project progress, discuss challenges, and seek feedback. | ------------- | -------------
Senior Leaders | Status Debrief | One-time | Project Manager | One week after the delivery improvements are implemented | Email | Provide high-level update on project impact, delivery times, and overall customer satisfaction. | ------------- | -------------