## Sheet1
Gantt Chart
TITLE: Beta "T.B" for delivering orders and products
Name: George Youssef Ward Issa
| TASK ID | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1
[8 empty] | 2025-01-01 | [19 empty] | 2025-02-01 | [19 empty] | 2025-03-01 | [19 empty] | 2025-04-01 | [19 empty] | 2025-05-01 | [19 empty] | 2025-06-01 | [19 empty] | 2025-07-01 | [19 empty] | 2025-08-03 | [19 empty] | 2025-09-01 | [19 empty] | 2025-10-05 | [19 empty] | 2025-11-02 | [19 empty] | 2025-12-01 | [19 empty] | 2026-01-04 | [19 empty] | 2026-02-01 | [19 empty] | 2026-03-01 | [19 empty] | 2026-04-05 | [19 empty] | 2026-05-03 | [19 empty] | 2026-06-01 | [19 empty] | 2026-07-01
[8 empty] | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | M | T | W | T | S | W | T | S | M | T
[8 empty] | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 2024-05-01 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 1 | 2 | 5 | 6 | 7
Milestone | 1 | Improving order delivery | bar: 2025-01-01 S 5
Main Task | 1.1 | Increasing Delivery Capacity
Subtasks | 1.1.1 | Modern delivery devices | Financial sponsor | 2024-01-05 | Jan 30 | 20 | 0% | bar: 2025-01-01 S 5
| 1.1.2 | Additional delivery workers | HR Manager | 2024-02-02 | 2024-03-06 | 25 | 0% | bar: 2025-02-01 S 2
| 1.1.3 | Work distribution system | IT Team | 2024-03-09 | 2025-05-08 | 40 | 0% | bar: 2025-03-01 S 9
| 1.1.4 | Training on efficient routes and time management | Training Manager | 2024-03-09 | 2025-03-27 | 15 | 0% | bar: 2025-03-01 S 9
| 1.1.5 | Timely order arrivals and responsive customer service | Sales Manager | 2025-05-11 | 2025-06-26 | 35 | 0% | bar: 2025-05-01 S 11
Main Task | 1.2 | Enhancing Order Processing
Subtasks | 1.2.1 | Increased number of call receptionists | HR Manager | 2025-07-06 | 2025-07-24 | 15 | 0% | bar: 2025-07-01 S 6
| 1.2.2 | Upgraded call reception technology | Financial sponsor | 2025-07-06 | 2025-07-31 | 20 | 0% | bar: 2025-07-01 S 6
| 1.2.3 | AI-powered software | IT Team | 2025-07-06 | 2025-09-28 | 60 | 0% | bar: 2025-07-01 S 6
| 1.2.4 | Tracking system for inquiries and orders | IT Team | 2025-10-05 | 2025-12-14 | 50 | 0% | bar: 2025-10-05 S 5
Milestone | 2 | Ensuring accurate order delivery
Main Task | 2.1 | Improving Address Verification
Subtasks | 1.1.1 | GPS technology verification | IT Team | 2025-10-05 | 2025-11-20 | 35 | 0% | bar: 2025-10-05 S 5
| 1.1.2 | Online form for address input | IT Team | 2025-10-05 | 2025-11-06 | 25 | 0% | bar: 2025-10-05 S 5
| 1.1.3 | Confirmation system for order details | IT Team | 2025-10-05 | 2025-11-19 | 35 | 0% | bar: 2025-10-05 S 5
Main Task | 2.2 | Monitoring Delivery Performance
Subtasks | 1.2.1 | Establishment of KPIs | Business Analyst | 2025-10-05 | 2025-10-30 | 20 | 0% | bar: 2025-10-05 S 5
| 1.2.2 | Regular reviews of performance data | Data Analyst | 2025-12-15 | 2026-01-22 | 25 | 0% | bar: 2025-12-01 M 15
| 1.2.3 | Customer feedback solicitation | Marketing Team | 2026-01-25 | 2026-02-12 | 15 | 0% | bar: 2026-01-04 S 25
Milestone | 3 | Ensuring accurate order delivery
Main Task | 3.1 | Improving Communication Channels
Subtasks | 3.1.1 | Expanded customer service hours | Technical Manager | 2026-06-15 | 2026-06-21 | 5 | 0% | bar: 2026-06-01 M 15
| 3.1.2 | Live chat option | IT Team | 2026-03-22 | 2026-05-28 | 45 | 0% | bar: 2026-03-01 S 22
| 3.1.3 | Training for customer service representatives | Training Manager |  |  | 10 | 0% | bar: 2026-06-01 M 22
Main Task | 3.2 | Gathering Customer Feedback
Subtasks | 3.2.1 | Surveys on customer satisfaction | IT Team | 2026-02-15 | 2026-02-19 | 5 | 0% | bar: 2026-02-01 S 15
| 3.2.2 | Feedback data analysis | Data Analyst | 2026-02-22 | 2026-03-19 | 20 | 0% | bar: 2026-02-01 S 22
| 3.2.3 | Implementation of changes based on feedback | Technical Manager | 2026-03-22 | 2026-06-14 | 55 | 0% | bar: 2026-03-01 S 22